## M2
Milestone 2 |  | Dev Status | Client Status | Summission Date | Approval Date
Sr. Number | Modules
1 | Logo Design | Done | Done
2 | Design | Done | Done
3 | Project Plan | In progress | In progress
Sr. Number | Admin
1 | Login | In progress | Not Started
2 | Forgot Password | In progress | Not Started
3 | Change Password | In progress | Not Started
4 | Keep Sign in | Not Started | Not Started
5 | My Profile | Not Started | Not Started
7 | App Slider Management- Slider Templates | Not Started | Not Started
8 | Faq Management | Not Started | Not Started
9 | Blog Management | Not Started | Not Started
11 | User Management | Not Started | Not Started
13 | CMS Pages | Not Started | Not Started
14 | Logout | Not Started | Not Started
15 | Testing | Not Started | Not Started
16 | Client Feedback | Not Started | Not Started

## M3
Milestone 3 |  | Dev Status | Client Status | Summission Date | Approval Date
Sr. Number | Application
1 | Splash Screen | In progress | Not Started
2 | Complete design integration | In progress | Not Started
3 | Introduction Screen - Dynamic Customer Frontend Developer | Not Started | Not Started
4 | User Signup Customer | Not Started | Not Started
5 | User Login Customer | Not Started | Not Started
6 | Customer Location (Customers can enable or disable location tracking.) | Not Started | Not Started
7 | Customer Profile (API inegration for personal & family details) | Not Started | Not Started
8 | Customer Profile (API inegration for education & occupation screen) | Not Started | Not Started
9 | Customer Profile (API inegration for profile verification screen) | Not Started | Not Started
10 | Customer Profile (API inegration for profile picture) | Not Started | Not Started
11 | Customer Profile (API inegration for gallery picture) | Not Started | Not Started
12 | Customer Profile (API inegration for hobbies screen) | Not Started | Not Started
13 | Customer Profile (API inegration for (drink, smoke and lifestyle screen) | Not Started | Not Started
14 | Customer Profile (API inegration for (diet preference, dress style screen) | Not Started | Not Started
15 | Social Signup with facebook, google and Apple | Not Started | Not Started
16 | Social Signup with google | Not Started | Not Started
17 | Social Signup with Apple | Not Started | Not Started
18 | Home screen- API integration for testimonail and blog section | Not Started | Not Started
19 | Home screen- filter data according to distance,age and parterner preference(Gender) | Not Started | Not Started
20 | My profile ( API integration for profile complete screen) | Not Started | Not Started
21 | Terms & Conditions | Not Started | Not Started
22 | Privacy Policy | Not Started | Not Started
23 | API integration for partner preference (basic) screen | Not Started | Not Started
24 | API integration for partner preference (education and occupation) screen | Not Started | Not Started
25 | API integration for partner preference (drink, smoke and diet) screen | Not Started | Not Started
26 | Testing | Not Started | Not Started
27 | Client Feedback | Not Started | Not Started
Sr. Number | Admin
28 | Subscription/ Membership Management | Not Started | Not Started
29 | Payment Management | Not Started | Not Started
30 | Ratings & Reviews Management (User Complaints Management) | Not Started | Not Started
31 | Dashboard | Not Started | Not Started
32 | User can view active package | Not Started | Not Started
33 | Content Management | Not Started | Not Started
34 | Message Module | Not Started | Not Started
35 | Report & Statistics | Not Started | Not Started
36 | Global Setting | Not Started | Not Started
37 | Logout | Not Started | Not Started
38 | Testing | Not Started | Not Started
39 | Client Feedback | Not Started | Not Started

## M4
Milestone 4 |  | Dev Status | Client Status | Summission Date | Approval Date
Sr. Number | Application
1 | User can save the card detail | Not Started | Not Started
2 | Search reasult show API integration as per the preference | Not Started | Not Started
3 | Action (block, save , send request,report, send picture request) API inetration on search result screen | Not Started | Not Started
4 | Result detail screen API integration | Not Started | Not Started
5 | Received ineterest screen API integration | Not Started | Not Started
6 | Home screen (sent and received) interest API integration | Not Started | Not Started
7 | In home screen apply filter API integrtion | Not Started | Not Started
8 | chat list API integration | Not Started | Not Started
9 | chat feature(send location,camera and photo) functionality | Not Started | Not Started
10 | Audio and video call feature | Not Started | Not Started
11 | Accepted and declined request listing API integration | Not Started | Not Started
12 | Subscription - Payment Integration | Not Started | Not Started
13 | User can receve push notifications | Not Started | Not Started
14 | User can view notifications | Not Started | Not Started
15 | Logout | Not Started | Not Started
Sr. Number | Delivery
1 | Upload on Server | Not Started | Not Started
2 | Complete Testing on Server | Not Started | Not Started